## Feature List
Robotic Grasping - Feature List
Feature No. | Feature Name | Summary | Complexity (1 - 5) | Iteration | Completion | Extra Details
1 | Visualise Dataset | Visualise the data provided by ACRONYM to get a better understanding. | 3 | 1 | Completed | Need to create watertight models so ACRONYM scripts can read.
2 | Generate Dataset | Using the ACRONYM data and modified scripts, generate images linked to grasps in .csv files. | 3 | 1 | Completed
3 | Gazebo Models | Using the ShapeNetSem .obj database, generate model .sdf files for Gazebo. | 2 | 2 | Completed
4 | Simulation Environment | Develop a Gazebo world with the Panda arm, kinect camera, and table. | 2 | 1 | Completed | Write a ROS node that sets up the Moveit! planning scene. Try to replicate environment from ACRONYM.
5 | Arm Manipulation Setup | Write prototype ROS nodes that deal with arm manipulation and grasping, and set up the planning interface in the environment. | 4 | 2 | Completed
6 | CNN configuration | Build the network structure using Tensorflow ready to train on the data. | 5 | 3 | Completed
7 | Train Network | Training the CNN on the dataset. | 4 | 3 | Partial | Not necessarily a feature, but important to note.
8 | Network Integration | Integrate Tensorflow prediction methods into the ROS environment. | 3 | 3 | Completed | Perhaps as a service?
9 | Develop Experiments | Develop ROS pipeline to run experiments on the trained network and evaluate grasp success. | 5 | 4 | Partial
10 | Save Results | Get results by running the experiments and save them as .csv files. | 2 | 4 | Unstarted
11 | Results Visualisation | Write script to generate graphs to visualise the results of the experiments. | 1 | 5 | Unstarted | This will be done alongside of writing the report.

## Gantt
Robotic Grasping - Gantt Chart
Task | Expected Start Week | Expected Duration (weeks) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Iteration 0 - Background Research
Read papers on grasping and CNNs | 1 | 1.5 | bar: Week 1
Setup Workspace | 1 | 1 | bar: Week 1
Find grasp dataset options | 1 | 2 | bar: Week 1 to Week 2
Create plan and overall model | 1 | 1 | bar: Week 1
Iteration 1
Visualise data | 3 | 1 | bar: Week 3
Generate Dataset | 3 | 2 | bar: Week 3 to Week 4
Simulation Environment | 3 | 2 | bar: Week 3 to Week 4
Iteration 2
Gazebo Models | 5 | 2 | bar: Week 5 to Week 6
Arm Manipulation Setup | 5 | 2 | bar: Week 5 to Week 6
Iteration 3
CNN Configuration | 7 | 2 | bar: Week 7 to Week 8
CNN Training | 8 | 3 | bar: Week 8 to Week 10
CNN Integration | 9 | 1 | bar: Week 9
Iteration 4
Develop Experiments | 10 | 2 | bar: Week 10 to Week 11
Iteration 5
Conduct Experiments | 12 | 2 | bar: Week 12 to Week 13
Visualise Results | 13 | 1 | bar: Week 13

## Testing
Robotic Grasping - Test Table
Test No. | Test Name | Feature No. | Description | Automated/Visual | Pass
1 | File names | 1 | A test to check that the images and grasp files are being saved with the correct name format. | Visual
2 | File matches | 1 | A test to ensure that the generated images have a corresponding grasp file. | Automated
3 | Image Exists | 2, 7 | A test to check that all the images are in the required folder. | Automated
4 | Tensor Data | 7 | A test to check that the grasp data is turned into the correct Tensor slice. | Automated
5 | Transform | 4 | Check that the transform tree poses are correct. | Visual
6 | Model Spawning | 3, 4 | Check that model spawns ate the required location. | Visual
7 | Prediction Service | 8 | Check that the pose predicted by the network matches the pose being used to grasp. | Automated
8 | End Effector Pose | 5 | Check that the arm is moving to the correct location in the scene. | Visual
9 | Image Scene | 4 | Check that the scene matches that in the dataset images. | Visual
10 | Results Format | 10, 11 | Check that the results are being saved correctly | Automated
11 | Grasp Success | 9 | Check that the grasp successes are being recorded correctly. | Visual